## Phases
BitForge: Open-Source Tool Map by Phase (solo schedule)
Blue = editable inputs. Work item counts and progress are formulas driven by the Tool Map status column.
Phase | Name | Start | End | Planned hours | Work items | Done | In progress | % done
P0 | Setup and specs (front-end only) | 2026-10-05 | 2026-10-18 | 50 | 9 | 0 | 0 | 0%
P1 | Single-lane core and IHP synthesis | 2026-10-19 | 2026-11-08 | 75 | 14 | 0 | 0 | 0%
P2 | Two lanes and host interface (front-end) | 2026-11-09 | 2026-11-29 | 75 | 11 | 0 | 0 | 0%
P3 | Verification depth (front-end) | 2026-11-30 | 2026-12-20 | 75 | 12 | 0 | 0 | 0%
P4 | Front-end closure and docs | 2026-12-21 | 2027-01-03 | 40 | 8 | 0 | 0 | 0%
P5 | Back-end: place-and-route, sign-off and submission | 2027-01-04 | 2027-01-18 | 50 | 14 | 0 | 0 | 0%
Total |  |  |  | 365 | 68 | 0 | 0 | 0%
Notes
Revision 3: front-end only in P0. Tiny Tapeout IHP synthesis (flow setup, tile size, first synthesis, area baseline) moves to P1 and is re-run for area in P2 and P3. Place-and-route, timing sign-off, DRC/LVS, gate-level smoke tests and GDS stay in P5. See the Moved Items sheet.
Source: solo schedule (25 h/week assumption). Hours and dates are planning values and are editable; they were not re-balanced. P1 gains about 8 to 10 hours of synthesis setup work, so consider adding hours to P1.
RISK: place-and-route and timing are still first measured in P5. Synthesis gives an early area signal but not timing or routability.
Whether Verilator 5.052 handles the IHP cell models, SVA, covergroups and the register model is unconfirmed; the P0 UVM spike (UVM-047) covers all but the cell models, which P1 checks.
GitHub and GitHub Actions are not open source; the plan uses Forgejo with Forgejo Actions, or Woodpecker CI.
(stretch) = only if the previous phase finished on time.

## Tool Map
ID | Phase | Dates | Work item | Requirement IDs | Tools | How the tool is used | Owner | Status | Notes
P0-01 | P0 | 10-05 to 10-18 | Create the repo and baselines | OSS-001, CHG-030 | Git | Repo, branches, tags such as base-isa-v0.1 | Me | Not started
P0-02 | P0 | 10-05 to 10-18 | Reproducible front-end toolchain | UVM-049 | Docker (or Nix) | Container pinning the front-end tools; synthesis tools added in P1, place-and-route and sign-off tools in P5 | Me | Not started
P0-03 | P0 | 10-05 to 10-18 | Commit-time checks | NET-051, CHG-004 | pre-commit, Verible, Python | Naming lint; block commits that lack a CR ID | Me | Not started
P0-04 | P0 | 10-05 to 10-18 | Freeze the ISA spec | ISA-018 | Python, PyYAML | Validate isa.yaml (opcode overlaps, field widths) | Me | Not started
P0-05 | P0 | 10-05 to 10-18 | Freeze the register map | HIF-010 | Python, PyYAML, Jinja2 | Validate regmap.yaml; generate first register table | Me | Not started
P0-06 | P0 | 10-05 to 10-18 | Lint the RTL | RTL-005 | Verilator, Verible | Verilator --lint-only -Wall; zero-warning rule from day one | Me | Not started
P0-07 | P0 | 10-05 to 10-18 | UVM spike | UVM-047 | Verilator, Z3, UVM library, GCC | Tiny UVM test: virtual-interface agent, randomize() with {}, covergroup with cross, register model, DPI-C, bound SVA module | Me | Not started
P0-08 | P0 | 10-05 to 10-18 | Draft the module specs | ARC-011, SPC-001 | Pandoc | Section-based spec skeletons following the spec policy | Me | Not started
P0-09 | P0 | 10-05 to 10-18 | Waveform viewing |  | GTKWave, Surfer | View spike output | Me | Not started
P1-01 | P1 | 10-19 to 11-08 | Lane datapath, decode, imem, I/O synchronizer | ARC-001, ARC-002, ISA-001 to 010, IO-005 | Verilator, Verible | Write and lint the RTL | Me | Not started
P1-02 | P1 | 10-19 to 11-08 | Assembler | SW-001 | Python, pytest | Text-to-binary assembler driven by isa.yaml; unit test per opcode | Me | Not started
P1-03 | P1 | 10-19 to 11-08 | Cycle-accurate ISS | SW-003, DIF-007 | GCC, CMake | Reference model matching the RTL cycle for cycle | Me | Not started
P1-04 | P1 | 10-19 to 11-08 | ISS pin waveforms | SW-003 | GCC, GTKWave, Surfer | ISS writes VCD; view expected pin timing | Me | Not started
P1-05 | P1 | 10-19 to 11-08 | UVM skeleton | UVM-001 to 006 | Verilator, UVM library | Environment, interfaces, config, logging (--timing --binary) | Me | Not started
P1-06 | P1 | 10-19 to 11-08 | SPI host agent and pin agent | UVM-007, UVM-008 | Verilator, UVM library | Driver, monitor, sequences | Me | Not started
P1-07 | P1 | 10-19 to 11-08 | UART partner agent and UART firmware | UVM-009, PRO-001 | Verilator, UVM library, Python | Run assembled firmware on the DUT against a UART partner | Me | Not started
P1-08 | P1 | 10-19 to 11-08 | Directed opcode tests | UVM-023 | Verilator, Python | One test per opcode, tracked by seed | Me | Not started
P1-09 | P1 | 10-19 to 11-08 | Smoke regression | UVM-029, UVM-040 | GNU Make, Python, Forgejo, Woodpecker CI | One command and a CI job | Me | Not started
P1-10 | P1 | 10-19 to 11-08 | Timing diagrams for the spec | SPC-014 | WaveDrom | Cycle-by-cycle instruction diagrams | Me | Not started
P1-11 | P1 | 10-19 to 11-08 | Get the Tiny Tapeout IHP flow running (synthesis) | CON-001 | Tiny Tapeout IHP template, LibreLane, Docker | Add synthesis tools to the container; build the unchanged template through synthesis | Me | Not started
P1-12 | P1 | 10-19 to 11-08 | Set the 6x4 tile size | CON-002 | Tiny Tapeout IHP template | Set tile size in info.yaml | Me | Not started
P1-13 | P1 | 10-19 to 11-08 | First synthesis and area baseline | PHY-004, CON-004 | Yosys, LibreLane | Synthesize the single-lane RTL; record cell count against the 65% area budget | Me | Not started
P1-14 | P1 | 10-19 to 11-08 | Gate-level cell-model feasibility check | UVM-038 | Verilator, IHP PDK cell models, Yosys | Try elaborating the synthesized netlist and standard-cell models in Verilator (unconfirmed) | Me | Not started
P2-01 | P2 | 11-09 to 11-29 | Second lane, crossbar, conflict policy, open drain | ARC-001, IO-001 to 004 | Verilator, Verible | RTL and lint | Me | Not started
P2-02 | P2 | 11-09 to 11-29 | FIFOs, event flags, sync start | ARC-003, 005, 007, 009 | Verilator, Verible | RTL and lint | Me | Not started
P2-03 | P2 | 11-09 to 11-29 | Host SPI slave and registers | HIF-001 to 004, 006, 009 | Verilator, Verible | RTL and lint | Me | Not started
P2-04 | P2 | 11-09 to 11-29 | Register-model generation | UVM-015, HIF-010 | Python, Jinja2 | Generate UVM register model and datasheet table from regmap.yaml | Me | Not started
P2-05 | P2 | 11-09 to 11-29 | Register tests | UVM-015 | Verilator, UVM library | Reset-value and bit-bash tests | Me | Not started
P2-06 | P2 | 11-09 to 11-29 | SPI and I2C partner agents | UVM-010, UVM-011 | Verilator, UVM library | Partner models with error injection | Me | Not started
P2-07 | P2 | 11-09 to 11-29 | SPI/I2C firmware and two-lane demo | PRO-002, 003, 011 | Python | Assemble and simulate firmware with the assembler and ISS | Me | Not started
P2-08 | P2 | 11-09 to 11-29 | FIFO and protocol scoreboards | UVM-018, UVM-019 | Verilator, UVM library | Data and ordering checks | Me | Not started
P2-09 | P2 | 11-09 to 11-29 | Host Python library | SW-004 | Python, pytest | Load programs and read FIFOs; test against simulation | Me | Not started
P2-10 | P2 | 11-09 to 11-29 | Block diagrams | SPC-013 | Graphviz, Mermaid | Diagrams using names from the RTL | Me | Not started
P2-11 | P2 | 11-09 to 11-29 | Re-run synthesis for area (no place-and-route) | PHY-004 | Yosys, LibreLane | Area and flip-flop count after the second lane, FIFOs and host interface | Me | Not started
P3-01 | P3 | 11-30 to 12-20 | DPI reference-model scoreboard | UVM-016, UVM-017 | Verilator, GCC | Compare PC, registers and pins every cycle against the C ISS | Me | Not started
P3-02 | P3 | 11-30 to 12-20 | Constrained-random instruction generator | UVM-022 | Verilator, Z3, Python | Legal random programs from isa.yaml; set VERILATOR_SOLVER as needed | Me | Not started
P3-03 | P3 | 11-30 to 12-20 | Covergroups | UVM-031, UVM-032 | Verilator | Opcode, JMP, FIFO and pin coverage (--coverage) | Me | Not started
P3-04 | P3 | 11-30 to 12-20 | Coverage merge and reports | UVM-041 | verilator_coverage, Python | Merge across seeds; closure report | Me | Not started
P3-05 | P3 | 11-30 to 12-20 | SVA assertions | UVM-034 | Verilator | Checks on FIFO, FSM, reset and pin conflicts via bound SV modules | Me | Not started
P3-06 | P3 | 11-30 to 12-20 | Optional formal checks (stretch) | UVM-036 | SymbiYosys, Yosys | FIFO properties only; SymbiYosys supports a subset of SVA | Me | Not started
P3-07 | P3 | 11-30 to 12-20 | HIF stress, reset, fault and multi-lane tests | UVM-025 to 028 | Verilator, UVM library | Random and directed tests | Me | Not started
P3-08 | P3 | 11-30 to 12-20 | Timing checker (stretch) | UVM-020 | Verilator, UVM library | Compare edge intervals with ISA cycle counts | Me | Not started
P3-09 | P3 | 11-30 to 12-20 | JTAG/SWD reference hosts (stretch) | PRO-004, PRO-005 | OpenOCD, pyOCD | Reference hosts to check JTAG/SWD behavior | Me | Not started
P3-10 | P3 | 11-30 to 12-20 | Debug failing seeds |  | GTKWave, Surfer | Waveforms from failing seeds | Me | Not started
P3-11 | P3 | 11-30 to 12-20 | Re-run synthesis for area (no place-and-route) | PHY-004 | Yosys, LibreLane | Area check after each feature merge | Me | Not started
P3-12 | P3 | 11-30 to 12-20 | MIN profile fallback proven (synthesis only) | PHY-006 | Yosys, LibreLane | Prove the small profile fits if STD does not | Me | Not started
P4-01 | P4 | 12-21 to 01-03 | Coverage holes | UVM-033 | verilator_coverage, Python, Verilator | Find holes, add tests, record exclusions | Me | Not started
P4-02 | P4 | 12-21 to 01-03 | Synthesizable-subset review | RTL-001, RTL-002 | Verible, Verilator | Code review and lint for the Verilog-2005 synthesizable rules; complements the synthesis runs from P1 | Me | Not started
P4-03 | P4 | 12-21 to 01-03 | Front-end freeze and RTL release candidate | CHG-030, CHG-031 | Git, GNU Make | Tag the RTL candidate after full regression | Me | Not started
P4-04 | P4 | 12-21 to 01-03 | Protocol rate table (target clock) | TIM-006 | Python, Jinja2 | Generate from regression results; update with real fmax in P5 | Me | Not started
P4-05 | P4 | 12-21 to 01-03 | Datasheet build (draft) | OSS-002, DSU-003, DSU-022 | Pandoc, Python, Jinja2, WeasyPrint | Generate tables from YAML; CI compares with committed copy | Me | Not started
P4-06 | P4 | 12-21 to 01-03 | Diagrams and timing figures |  | Graphviz, Mermaid, WaveDrom | Figures | Me | Not started
P4-07 | P4 | 12-21 to 01-03 | Tutorial | OSS-003 | Pandoc, Python | UART in 10 instructions with a runnable example (assembler and ISS) | Me | Not started
P4-08 | P4 | 12-21 to 01-03 | Verification plan sign-off (front-end) | UVM-045 | Python, Git | Trace script checks every requirement has a test | Me | Not started
P5-01 | P5 | 01-04 to 01-18 | Run the full RTL-to-GDS flow with the real RTL | CON-001 | Tiny Tapeout IHP template, LibreLane, Docker | Add place-and-route and sign-off tools to the container; run the full flow | Me | Not started
P5-02 | P5 | 01-04 to 01-18 | RTL fixes from place-and-route findings | CHG-020, CHG-022 | Verilator, Verible, Git | Change requests for timing or congestion problems; rerun regression | Me | Not started
P5-03 | P5 | 01-04 to 01-18 | First place-and-route trial | PHY-002 | LibreLane, OpenROAD, Yosys | Full flow on the 6x4 tile | Me | Not started
P5-04 | P5 | 01-04 to 01-18 | Timing and layout checks | PHY-003 | OpenSTA, KLayout | Slack report and layout inspection | Me | Not started
P5-05 | P5 | 01-04 to 01-18 | Gate-level smoke tests | UVM-038 | Yosys, LibreLane, Verilator, IHP PDK cell models | Zero-delay functional run of gls_smoke; timing comes from STA | Me | Not started
P5-06 | P5 | 01-04 to 01-18 | Timing sign-off | PHY-003 | OpenSTA | Setup and hold at the target clock | Me | Not started
P5-07 | P5 | 01-04 to 01-18 | Area check | PHY-001 | Yosys, LibreLane | Final area at or below 65% of nominal tile area | Me | Not started
P5-08 | P5 | 01-04 to 01-18 | DRC | PHY-002 | KLayout, Magic | Clean DRC on final GDS; Magic is an optional second check | Me | Not started
P5-09 | P5 | 01-04 to 01-18 | LVS | PHY-002 | KLayout, Netgen | Layout matches netlist | Me | Not started
P5-10 | P5 | 01-04 to 01-18 | Final GDS | PHY-002 | LibreLane, OpenROAD | Final run and artifacts | Me | Not started
P5-11 | P5 | 01-04 to 01-18 | Datasheet numbers update | DSU-014, TIM-001, TIM-006 | Python, Jinja2, Pandoc | Insert real fmax, area and rate table; cite report names | Me | Not started
P5-12 | P5 | 01-04 to 01-18 | Power estimate (stretch) | PHY-005 | OpenROAD | Estimate only | Me | Not started
P5-13 | P5 | 01-04 to 01-18 | Final regression and release | OSS-004 | GNU Make, Forgejo, Woodpecker CI, Git | rel-v1.0 tag with datasheet hash recorded | Me | Not started
P5-14 | P5 | 01-04 to 01-18 | Submission package | CON-006 | Git, LibreLane, Tiny Tapeout IHP template | Final repo for Tiny Tapeout submission | Me | Not started

## Intent
ID | Phase | Work item | Requirement IDs | Intent (why this work item exists)
P0-01 | P0 | Create the repo and baselines | OSS-001, CHG-030 | Create one traceable source of truth so every change, baseline and release can be reproduced and audited.
P0-02 | P0 | Reproducible front-end toolchain | UVM-049 | Make every build and simulation reproducible with identical tool versions, so results do not depend on the machine.
P0-03 | P0 | Commit-time checks | NET-051, CHG-004 | Catch naming and change-control violations at commit time, when they are cheapest to fix.
P0-04 | P0 | Freeze the ISA spec | ISA-018 | Fix the instruction set as one machine-readable contract so the RTL, assembler, simulator and tests cannot drift apart.
P0-05 | P0 | Freeze the register map | HIF-010 | Fix the host-visible register contract early so RTL, register model, firmware library and datasheet come from one source.
P0-06 | P0 | Lint the RTL | RTL-005 | Keep the RTL clean and synthesizable from the first line instead of cleaning up a pile of warnings later.
P0-07 | P0 | UVM spike | UVM-047 | Learn in hours, not weeks, whether Verilator 5.052 can run the planned UVM environment, and choose the fallback early if not.
P0-08 | P0 | Draft the module specs | ARC-011, SPC-001 | Write down each block's intended behavior before coding so implementation and tests have a reference and design errors surface in review.
P0-09 | P0 | Waveform viewing | - | Confirm waveform debugging works from the start so failures can be inspected without delay.
P1-01 | P1 | Lane datapath, decode, imem, I/O synchronizer | ARC-001, ARC-002, ISA-001 to 010, IO-005 | Build the core lane engine that executes instructions in deterministic single cycles, the foundation everything else depends on.
P1-02 | P1 | Assembler | SW-001 | Let firmware be written as text and turned into the exact binary the chip runs, so protocols are developed without hand-encoding opcodes.
P1-03 | P1 | Cycle-accurate ISS | SW-003, DIF-007 | Provide a cycle-accurate golden reference of what a lane should do, used for firmware development and as the scoreboard reference.
P1-04 | P1 | ISS pin waveforms | SW-003 | Show expected pin timing before running the RTL, to validate protocol firmware and make failures easy to compare.
P1-05 | P1 | UVM skeleton | UVM-001 to 006 | Create the reusable verification structure early so every later agent, sequence and test plugs into it.
P1-06 | P1 | SPI host agent and pin agent | UVM-007, UVM-008 | Provide the means to load programs, configure the chip, and drive and observe pins, which every test needs.
P1-07 | P1 | UART partner agent and UART firmware | UVM-009, PRO-001 | Prove the architecture end to end with the simplest protocol: firmware runs on the RTL and talks to an independent partner.
P1-08 | P1 | Directed opcode tests | UVM-023 | Confirm each instruction behaves as specified so later failures are not blamed on basic decode errors.
P1-09 | P1 | Smoke regression | UVM-029, UVM-040 | Give a fast pass/fail check on every commit so breakage is caught immediately.
P1-10 | P1 | Timing diagrams for the spec | SPC-014 | Document cycle-level behavior precisely so timing guarantees are unambiguous and testable.
P1-11 | P1 | Get the Tiny Tapeout IHP flow running (synthesis) | CON-001 | Prove the Tiny Tapeout IHP flow works in our environment before design effort depends on it.
P1-12 | P1 | Set the 6x4 tile size | CON-002 | Lock in the 6x4 area envelope that all budgets are measured against.
P1-13 | P1 | First synthesis and area baseline | PHY-004, CON-004 | Obtain a real cell-count and area baseline for the core to see how much of the budget remains.
P1-14 | P1 | Gate-level cell-model feasibility check | UVM-038 | Learn early whether gate-level simulation is practical with Verilator and the IHP cell models, so the plan can change if it is not.
P2-01 | P2 | Second lane, crossbar, conflict policy, open drain | ARC-001, IO-001 to 004 | Add multi-lane operation and flexible pin assignment so protocols needing a clock lane and a data lane are possible, with a defined outcome when lanes collide on a pin.
P2-02 | P2 | FIFOs, event flags, sync start | ARC-003, 005, 007, 009 | Let lanes exchange data with the host, coordinate with each other, and start together on the same clock edge.
P2-03 | P2 | Host SPI slave and registers | HIF-001 to 004, 006, 009 | Give the outside world one controlled path to load programs, configure the chip and read data.
P2-04 | P2 | Register-model generation | UVM-015, HIF-010 | Keep registers consistent across RTL, tests and datasheet by generating them from a single source.
P2-05 | P2 | Register tests | UVM-015 | Verify the register interface matches the spec, catching reset-value and access bugs early.
P2-06 | P2 | SPI and I2C partner agents | UVM-010, UVM-011 | Provide independent protocol partners that expose firmware errors, including bus-level corner cases such as clock stretching.
P2-07 | P2 | SPI/I2C firmware and two-lane demo | PRO-002, 003, 011 | Demonstrate the central goal: new protocols as firmware, including one that uses more than one lane.
P2-08 | P2 | FIFO and protocol scoreboards | UVM-018, UVM-019 | Check data and ordering automatically instead of relying on visual inspection.
P2-09 | P2 | Host Python library | SW-004 | Give users and tests a practical way to load firmware and operate the chip from a PC or microcontroller.
P2-10 | P2 | Block diagrams | SPC-013 | Make the architecture reviewable and keep the specification's names matching the RTL.
P2-11 | P2 | Re-run synthesis for area (no place-and-route) | PHY-004 | Check that added features have not blown the area budget while changes are still cheap.
P3-01 | P3 | DPI reference-model scoreboard | UVM-016, UVM-017 | Compare the RTL with the golden simulator every cycle so subtle timing and state errors are found automatically.
P3-02 | P3 | Constrained-random instruction generator | UVM-022 | Reach instruction sequences nobody thought to write by hand.
P3-03 | P3 | Covergroups | UVM-031, UVM-032 | Measure what has actually been tested so missing tests become visible.
P3-04 | P3 | Coverage merge and reports | UVM-041 | Combine results from many seeds into one view for closure decisions.
P3-05 | P3 | SVA assertions | UVM-034 | Encode design rules as always-on checks so violations are flagged the moment they occur.
P3-06 | P3 | Optional formal checks (stretch) | UVM-036 | Prove selected properties for all inputs where simulation can only sample (stretch).
P3-07 | P3 | HIF stress, reset, fault and multi-lane tests | UVM-025 to 028 | Test robustness against unusual host behavior, resets and multi-lane contention.
P3-08 | P3 | Timing checker (stretch) | UVM-020 | Verify the cycle-exact timing promise independently of the scoreboard (stretch).
P3-09 | P3 | JTAG/SWD reference hosts (stretch) | PRO-004, PRO-005 | Check the optional protocols against real-world reference implementations (stretch).
P3-10 | P3 | Debug failing seeds | - | Make failures reproducible and diagnosable from their seeds.
P3-11 | P3 | Re-run synthesis for area (no place-and-route) | PHY-004 | Keep area in check as verification-driven fixes and features land.
P3-12 | P3 | MIN profile fallback proven (synthesis only) | PHY-006 | Ensure a smaller fallback design is known to fit if the standard one does not.
P4-01 | P4 | Coverage holes | UVM-033 | Close the gap between 'tests pass' and 'tested enough' with targeted tests or documented exclusions.
P4-02 | P4 | Synthesizable-subset review | RTL-001, RTL-002 | Reduce the risk that RTL which simulates correctly misbehaves or fails in synthesis.
P4-03 | P4 | Front-end freeze and RTL release candidate | CHG-030, CHG-031 | Establish a stable, tagged RTL baseline so back-end work is not chasing a moving target.
P4-04 | P4 | Protocol rate table (target clock) | TIM-006 | Publish the speeds each protocol can really reach so users know the limits.
P4-05 | P4 | Datasheet build (draft) | OSS-002, DSU-003, DSU-022 | Create the user-facing contract while details are fresh, generated from the same sources as the RTL.
P4-06 | P4 | Diagrams and timing figures | - | Make the documentation understandable without reading the RTL.
P4-07 | P4 | Tutorial | OSS-003 | Prove a newcomer can write and run a new protocol using only the public documentation.
P4-08 | P4 | Verification plan sign-off (front-end) | UVM-045 | Show that every requirement is covered by a test, so completeness is evidenced rather than assumed.
P5-01 | P5 | Run the full RTL-to-GDS flow with the real RTL | CON-001 | Move from the empty template to the actual design for place-and-route and sign-off.
P5-02 | P5 | RTL fixes from place-and-route findings | CHG-020, CHG-022 | Provide a controlled way to fix problems found in physical design without destabilizing verified behavior.
P5-03 | P5 | First place-and-route trial | PHY-002 | Find out whether the design routes inside the 6x4 tile.
P5-04 | P5 | Timing and layout checks | PHY-003 | See where timing is tight and whether the layout is sane.
P5-05 | P5 | Gate-level smoke tests | UVM-038 | Confirm the synthesized netlist behaves like the RTL on the core protocols.
P5-06 | P5 | Timing sign-off | PHY-003 | Show the chip meets setup and hold at the target clock.
P5-07 | P5 | Area check | PHY-001 | Confirm the design fits the budget with margin for tool variation.
P5-08 | P5 | DRC | PHY-002 | Ensure the layout obeys foundry rules so it can be fabricated.
P5-09 | P5 | LVS | PHY-002 | Confirm the layout implements the intended netlist.
P5-10 | P5 | Final GDS | PHY-002 | Produce the file that goes to fabrication.
P5-11 | P5 | Datasheet numbers update | DSU-014, TIM-001, TIM-006 | Replace targets with measured values so the documentation is true to the chip.
P5-12 | P5 | Power estimate (stretch) | PHY-005 | Give users a rough power figure for board design (stretch).
P5-13 | P5 | Final regression and release | OSS-004 | Release only a state proven by a full regression pass, with an immutable tag.
P5-14 | P5 | Submission package | CON-006 | Deliver a complete, reproducible, open-source submission by the deadline.

## Tools
Tool | Category | P0 | P1 | P2 | P3 | P4 | P5 | Total work items | Match text
Git | Version control | 1 | 0 | 0 | 0 | 2 | 3 | 6 | Git
Docker (or Nix) | Environment | 1 | 1 | 0 | 0 | 0 | 1 | 3 | Docker
Tiny Tapeout IHP template | Physical flow | 0 | 2 | 0 | 0 | 0 | 2 | 4 | Tiny Tapeout IHP template
LibreLane | Physical flow | 0 | 2 | 1 | 2 | 0 | 6 | 11 | LibreLane
Yosys | Synthesis | 0 | 2 | 1 | 3 | 0 | 3 | 9 | Yosys
OpenROAD | Physical flow | 0 | 0 | 0 | 0 | 0 | 3 | 3 | OpenROAD
OpenSTA | Timing | 0 | 0 | 0 | 0 | 0 | 2 | 2 | OpenSTA
KLayout | Layout / DRC / LVS | 0 | 0 | 0 | 0 | 0 | 3 | 3 | KLayout
Magic | Layout / DRC | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Magic
Netgen | LVS | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Netgen
IHP PDK cell models | PDK | 0 | 1 | 0 | 0 | 0 | 1 | 2 | IHP PDK cell models
Verilator | Simulation / lint / coverage | 2 | 6 | 6 | 7 | 2 | 2 | 25 | Verilator
verilator_coverage | Coverage | 0 | 0 | 0 | 1 | 1 | 0 | 2 | verilator_coverage
UVM library | Verification | 1 | 3 | 3 | 2 | 0 | 0 | 9 | UVM library
Z3 | Constraint solver | 1 | 0 | 0 | 1 | 0 | 0 | 2 | Z3
SymbiYosys | Formal | 0 | 0 | 0 | 1 | 0 | 0 | 1 | SymbiYosys
GCC | C toolchain | 1 | 2 | 0 | 1 | 0 | 0 | 4 | GCC
CMake | C toolchain | 0 | 1 | 0 | 0 | 0 | 0 | 1 | CMake
GNU Make | Build | 0 | 1 | 0 | 0 | 1 | 1 | 3 | GNU Make
Python | Scripting | 3 | 4 | 3 | 2 | 5 | 1 | 18 | Python
PyYAML | Scripting | 2 | 0 | 0 | 0 | 0 | 0 | 2 | PyYAML
Jinja2 | Generation | 1 | 0 | 1 | 0 | 2 | 1 | 5 | Jinja2
pytest | Testing | 0 | 1 | 1 | 0 | 0 | 0 | 2 | pytest
Verible | Lint | 2 | 1 | 3 | 0 | 1 | 1 | 8 | Verible
pre-commit | Quality gate | 1 | 0 | 0 | 0 | 0 | 0 | 1 | pre-commit
GTKWave | Waveforms | 1 | 1 | 0 | 1 | 0 | 0 | 3 | GTKWave
Surfer | Waveforms | 1 | 1 | 0 | 1 | 0 | 0 | 3 | Surfer
WaveDrom | Diagrams | 0 | 1 | 0 | 0 | 1 | 0 | 2 | WaveDrom
Graphviz | Diagrams | 0 | 0 | 1 | 0 | 1 | 0 | 2 | Graphviz
Mermaid | Diagrams | 0 | 0 | 1 | 0 | 1 | 0 | 2 | Mermaid
Pandoc | Documents | 1 | 0 | 0 | 0 | 2 | 1 | 4 | Pandoc
WeasyPrint | Documents | 0 | 0 | 0 | 0 | 1 | 0 | 1 | WeasyPrint
Forgejo | CI / tracker | 0 | 1 | 0 | 0 | 0 | 1 | 2 | Forgejo
Woodpecker CI | CI | 0 | 1 | 0 | 0 | 0 | 1 | 2 | Woodpecker CI
OpenOCD | Stretch protocols | 0 | 0 | 0 | 1 | 0 | 0 | 1 | OpenOCD
pyOCD | Stretch protocols | 0 | 0 | 0 | 1 | 0 | 0 | 1 | pyOCD
Counts are the number of Tool Map work items whose Tools cell mentions the tool (text match). Yosys also matches SymbiYosys, and Verilator also matches verilator_coverage.

## Moved Items
Item | Requirement IDs | v1 plan | v2 plan | v3 plan (now) | Effect / mitigation
Tiny Tapeout flow running | CON-001 | P0 | P5 | P1 | Template built through synthesis in P1; full flow with real RTL in P5
Set 6x4 tile size | CON-002 | P0 | P5 | P1 | Low risk
First synthesis and area baseline | PHY-004, CON-004 | P0 | P5 | P1 | Early area signal on the single-lane core
Gate-level cell-model feasibility check | UVM-038 | P0 | P5 | P1 | Elaborate the synthesized netlist and cell models in Verilator; result decides whether gate-level smoke tests in P5 are possible
Re-run synthesis for area at each merge | PHY-004 | P1 to P3 | P5 | P2 and P3 | Yosys and LibreLane synthesis only, no place-and-route
MIN profile fallback proven | PHY-006 | P3 | P5 | P3 | Synthesis only; routability still unknown
First place-and-route trial | PHY-002 | P2 | P5 | P5 | Routing congestion found late
Timing and layout checks | PHY-003 | P2 | P5 | P5 | Fmax unknown until P5; rate table in P4 uses the target clock
Gate-level smoke tests, timing sign-off, area check, DRC, LVS, final GDS | UVM-038, PHY-001 to 003 | P4 | P5 | P5 | P5 carries all place-and-route and sign-off closure
Datasheet build, figures, tutorial, vPlan sign-off | OSS-002, OSS-003, UVM-045 | P5 | P4 | P4 | Moved earlier to free P5; datasheet numbers updated in P5
Power estimate (stretch) | PHY-005 | P5 | P5 | P5 | Unchanged
Process note: moving milestone scope and revising PHY-004 and PHY-006 are Major changes under the development policies (CHG-002, CHG-031). Raise a CR and observe the 24-hour cooling-off.
Mitigation options if P5 looks too tight: (1) move the front-end freeze earlier, e.g. 12-13, and start P5 on 12-14; (2) run one early place-and-route trial after the P1 synthesis as a go/no-go check (about 2 to 3 hours); (3) pre-agree the MIN profile as the submission fallback.